TradeLoop

TASKBOARD

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Deliverable 1 — All Sprints (Completed) Community description, problem statement, survey design & execution (21 respondents), survey analysis, business idea, value proposition, and references. Submitted 13 March 2026. Deliverable 2 — Sprint 1 (Completed) Section 1: Improvements After Feedback — Reviewed Deliverable 1 feedback; improved survey sample size framing, product context clarity, and missing cost analysis. Section 2: Marketing Strategy (5 W’s) — WHO: customer personas (Nomsa & Lungelo); WHAT: TradeLoop service offering; WHERE: five marketing channels; WHEN: launch timing; WHY: competitor comparison and USP. Deliverable 2 — Sprint 2 (Completed) Section 3: Feasibility Analysis — Startup cost table (R26,500–R41,500), resource requirements, three risks (market, financial, operational) with mitigations, feasibility conclusion, and NYDA/SEDA funding research. Section 4: MVP Design — 4-step WhatsApp concierge testing approach, worker recruitment, consumer campaign, manual matching process, and five success metrics table. Deliverable 2 — Sprint 3 (Completed) References & Formatting — Stephan finalises document formatting, headers, branding, and referencing consistency. Final Proofreading & Submission — Ntombenhle checks all writing; Precious reviews coherence and submits Deliverable 2. Deliverable 3 — Sprint 1 (Completed) Review Deliverable 2 feedback. Begin business model canvas and financial projections for Deliverable 3. Deliverable 3 — Sprint 2 (Completed) Prototype / pitch deck development. Draft go-to-market plan and implementation roadmap. Deliverable 3 — Sprint 3 (Completed) Final formatting, referencing, proofreading, and submission of Deliverable 3. Guided Prototype Walkthrough — 21–24 July 2026 (Completed) Built a self-guided walkthrough panel for the TradeLoop interactive prototype covering both the Client and Worker journeys — mode toggle, sectioned steps (onboarding, posting a job, hiring & payment, review & account for Client; getting started, working a job, earnings & account for Worker), jump-to-screen navigation, search, and contextual tips for verification and escrow. Linked the live prototype into Deliverable 2’s MVP section and reference list. Completed 24 July 2026. |  |  |

WALKTHROUGH

| - What do we need to do to advance this piece of work? | Complete the Feasibility Analysis (startup costs, resources, risks, conclusion) and design the MVP testing plan with success metrics. These are the two remaining sections before final formatting and submission. |
| --- | --- |
| - Is anyone working on anything that is not on the board? | No. All teamwork is captured on the board. Stephan is finalizing the document design and layout while Ntombenhle handles writing and editing. Precious is coordinating and reviewing completed sections. |
| - What do we need to finish as a team? | Feasibility Analysis, MVP plan, final proofreading, and document submission by the deadline. |
| - Are there any bottlenecks or blockers to the flow of work? | Group availability varies throughout the week due to other module commitments. We need to coordinate writing and review windows carefully to avoid last-minute bottlenecks before submission. |

LOGBOOK

| Date: | 21-07-2026 |  |
| --- | --- | --- |
| Tuesday | - What did I complete since the last standup? | Went back into the TradeLoop prototype to plan a guided walkthrough — the app had grown a lot of screens and we agreed evaluators shouldn't need us in the room to understand the Client and Worker journeys. Mapped out the full click-path for both sides and grouped it into stages: onboarding, posting a job, hiring and payment, and review and account for the Client side; getting started, working a job, and earnings and account for the Worker side. |
|  | - What am I planning to complete between now and the next standup? | Stephan to build the guide panel shell — a side panel with Client and Worker mode tabs that sits alongside the prototype. I am drafting the step-by-step walkthrough text for each stage. Ntombenhle to start updating the Deliverable 2 wording so Section 4 references the live interactive prototype directly. |
|  | - What are my impediments (or risks or problems)? | Squeezing this into the same week as other module deadlines. Agreed to timebox the guide panel build to four days so it did not eat into other coursework. |
| Date: | 22-07-2026 |  |
| Wednesday | - What did I complete since the last standup? | Stephan built the Client/Worker mode toggle and the section layout for the guide panel. I drafted the walkthrough steps for the onboarding and job-posting stages, each one linked to a jump button that takes you straight to the matching screen in the prototype. |
|  | - What am I planning to complete between now and the next standup? | Finish drafting the remaining steps — hiring and payment, review and account, and the full Worker side. Add a search bar so anyone reviewing the prototype can jump straight to any screen by name. I am also writing short tips explaining the reasoning behind the trickier steps, like ID verification and escrow payment. |
|  | - What are my impediments (or risks or problems)? | Had to make sure the new step-highlighting did not interfere with the existing screen navigation we built earlier. Stephan tested every jump button individually to catch any broken links before we added more content. |
| Date: | 23-07-2026 |  |
| Thursday | - What did I complete since the last standup? | Finished all guide panel content for both Client and Worker modes and added the search bar. Clicking a step now highlights the matching part of the panel so it is obvious what you are looking at. I completed the tip text explaining why verification and escrow matter, not just what they do. |
|  | - What am I planning to complete between now and the next standup? | Full group run-through of the guided prototype to catch anything confusing or broken. Ntombenhle to proofread all the guide panel text for tone and grammar. I am finalising the prototype link and the wording to drop into Deliverable 2's MVP section and reference list. |
|  | - What are my impediments (or risks or problems)? | A few of my step descriptions were too long and got cut off in the panel. Agreed on a stricter word limit per step and rewrote the longest ones to fit. |
| Date: | 24-07-2026 |  |
| Friday | - What did I complete since the last standup? | Group did a full walkthrough of the guided prototype end to end on both the Client and Worker paths and confirmed everything worked. Ntombenhle finished proofreading the guide text. I added the live prototype link into Deliverable 2's MVP section and reference list and did a final coherence check on the updated document. |
|  | - What am I planning to complete between now and the next standup? | Share the updated Deliverable 2 document and the guided prototype link with the group for a last look before the next submission window. Start looking at what the next module deliverable needs from us. |
|  | - What are my impediments (or risks or problems)? | No major blockers this week. The main challenge was keeping the guide panel content concise, which we sorted out by holding a strict word limit per step. |